## Form List (hidden)
B. Human Resource | Start Date | End Date | Status | Remarks
1.1 Recruitment, Selection and Placement
1.2 Performance Management
1.3 Learning and Development
1.4 Rewards and Recognition
1.5 Attendance -Timekeeping
Forms | 2019-05-20
Batch DTR Entry
Others | 2019-05-20
Biometric Profiling
Others | 2019-05-21
Correction Time Log
Fig. 1.5.13 Correction of Time Log by Employee | 2019-05-21
CTO Entry
Others | 2019-05-22
Daily Time Record
Fig. 1.5.1-a CS Form No. 48 DTR Entry
Fig. 1.5.1-b.1 CS Form No. 48 DTR List
Fig. 1.5.1-b.2 CS Form No. 48 DTR Print | 2019-05-22
Holiday Setup
Fig. 1.5.12 Holiday Set-up | 2019-05-23
Incident Report
Fig. 1.5.2-a Incident Report – Form 1
Fig. 1.5.2-b Incident Report – Form 2 | 2019-05-23
Incomplete Logs
Others
Official Business
Fig. 1.5.4-c Application List Print | 2019-05-24
Overtime Application
Fig. 1.5.10-a Overtime Application | 2019-05-24
Fig. 1.5.10-b.1 Overtime Application List
Fig. 1.5.10-b.2 Overtime Application Print List
Fig. 1.5.10-b.3 Overtime Application Certification
Fig. 1.5.10-b.4 Overtime Justification
Pass Slip
Fig. 1.5.4-a Pass Slip Entry | 2019-05-25
Fig. 1.5.4-b Pass Slip List
Fig. 1.5.4-d Individual Pass Slip/Time Adjustment Slip– front
Fig. 1.5.4-e Individual Pass Slip/Time Adjustment Slip - back
Timeshift Setup
Fig. 1.5.11 Time Shift Schedule | 2019-05-25
Travel Order
Fig. 1.5.3 Travel Order
Report
Notice of Tardiness
Fig. 1.5.8 Notification of Tardiness to Department/Office Heads
Perfect Attendance
Fig. 1.5.7 Perfect Attendance
Punctuality Report and Frequency
Fig. 1.5.6 Punctuality Report and Frequency
Travel Order Report
Fig. 1.5.5 Travel Abroad
(blank)
Fig. 1.5.9 Flag Ceremony/Retreat/Mandatory Events - Attendance Monitoring
1.6 Leave Administration
1.7 Retirement and Other Personnel Services / Benefits
1.8 Complaints
1.9 Citizen’s Charter | 2019-05-20 | 2019-05-20
1.10 General Settings
(blank) | 2019-05-20 | 2019-05-20
LGU Name Setting
LGU Name Setting | 2019-05-20 | 2019-05-20
Department Setting
Department Setting | 2019-05-20 | 2019-05-20
Elected Officials
Elected Officials | 2019-05-20 | 2019-05-20
Barangay Setting
Barangay Setting
Header Setiings
Header Setiings
Grand Total

## Summary1 (hidden)
| Total | Prorgammer |  |  |  | QA
|  | Pending | Ongoing | Done | Fixing | Pending | Ongoing | Done | Bugs | Enhancement
1.1 Recruitment, Selection and Placement | 13 |  |  | 13 |  |  |  | 1 |  | 13 | Gilbert
1.2 Performance Management | 8 |  | 5 | 3 |  | 5 | 1 |  |  | 2 | sir ken
1.3 Learning and Development | 13 |  |  | 13 | [5 empty] | 13 | sir ken
1.4 Rewards and Recognition | 13 |  | 1 | 12 |  | 1 | 5 |  |  | 7 | sir ken
1.5 Attendance -Timekeeping | 23 |  | 1 | 22 |  |  | 1 |  |  | 22 | jayson
1.6 Leave Administration | 13 |  |  | 13 | [5 empty] | 13 | jayson
1.7 Retirement and Other Personnel Services / Benefits | 24 |  |  | 24 | [5 empty] | 24 | Gilbert
1.8 Complaints | 9 |  |  | 9 |  |  | 1 |  |  | 8 | sir ken
1.9 Citizens Charter | 13 |  |  | 13 |  |  |  | 13 |  |  | Gilbert
1.10 General Settings | 7 |  |  | 7 |  |  |  | 2 |  | 5
1.1a Administarive | 15 |  |  | 15 |  |  |  | 7 |  | 11 | jayason
| 151 | 0 | 7 | 144 | 0 | 6 | 8 | 23 |  | 118
|  |  | Done DEV | 144 |  |  | Done QA | 141

## Workload1 (hidden)
B. Human Resource |  |  | Programmer |  |  | QA
| Start Date | End Date | Owner | Status | Remarks | Owner | Status | Remarks
1.1 Recruitment, Selection and Placement |  |  | Gilbert |  |  | Gen
Applicants Entry |  |  |  | Done |  |  | Enhancement
Fig. 1.1.14-a Applicant Profile Form | 2019-05-21 | 2019-05-21 |  | Done
Fig. 1.1.14-b.1 Applicant Entry List | 2019-05-21 | 2019-05-21 |  | Done
Fig. 1.1.14-b.2 Applicant Print List | 2019-05-21 | 2019-05-21 |  | Done
Fig. 1.1.5-a.1 Appointment Processing Checklist | 2019-05-21 | 2019-05-21 |  | Done
Fig. 1.1.5-a.2 Appointment Processing Checklist | 2019-05-21 | 2019-05-21 |  | Done
Fig. 1.1.7 Notices | 2019-05-21 | 2019-05-21 |  | Done
Appoinment Transmittal |  |  |  | Done |  |  | Enhancement
Fig. 1.1.18 Appointment Transmittal and Action Form (CS Form No.1)/RAI | 2019-05-21 | 2019-05-21
Comparative Assessment |  |  |  | Done |  |  | Enhancement
Fig. 1.1.13-c Comparative Assessment | 2019-05-22 | 2019-05-22
Employee Profiling |  |  |  | Done |  |  | Enhancement
Fig. 1.1.1-a.1 Personal Data Sheet Entry Form (Basic Info) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-a.10 Personal Data Sheet Entry Form (References) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-a.11 Personal Data Sheet Entry Form (Employment Information) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-a.12 Leave Type | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-a.2 Personal Data Sheet Entry Form (Family Background) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-a.3 Personal Data Sheet Entry Form (Educational Background) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-a.4 Personal Data Sheet Entry Form (Civil Service Eligibility) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-a.5 Personal Data Sheet Entry Form (Work Experience) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-a.6 Personal Data Sheet Entry Form (Voluntary Work) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-a.7 Personal Data Sheet Entry Form (Training Programs) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-a.8 Personal Data Sheet Entry Form (Other Information) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-a.9 Personal Data Sheet Entry Form (Other Information) Cont. | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-b.1 Personal Data Sheet (CS Form No.212) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-b.2 Personal Data Sheet (CS Form No.212) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-b.3 Personal Data Sheet (CS Form No.212) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.1-b.4 Personal Data Sheet (CS Form No.212) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.2-a.1 Certificate of Appointment (CS Form No.33B) | 2019-05-23 | 2019-05-23 |  | Done
Fig. 1.1.2-a.2 Certificate of Appointment (CS Form No.33B) | 2019-05-23 | 2019-05-23 |  | Done
Manpower Request Summary |  |  |  | Done |  |  | Enhancement
Fig. 1.1.12 Manpower Request Summary | 2018-05-20 | 2018-05-20
Manpower Request/Reassignment |  |  |  | Done |  |  | Enhancement
Fig. 1.1.3 Manpower Request/Reassignment | 2018-05-20 | 2018-05-20
Personnel Scheduler |  |  |  | Done |  |  | Enhancement
Fig. 1.1.10 Personnel Schedule – Per Office | 2018-05-24 | 2018-05-24
Fig. 1.1.11 Personnel Schedule - Consolidated | 2018-05-24 | 2018-05-24
Fig. 1.1.13-a.1 Shortlisted Selection Line-UP (First Level Form A) | 2018-05-24 | 2018-05-24
Fig. 1.1.13-a.2 Shortlisted Selection Line-UP (First Level Form B) | 2018-05-24 | 2018-05-24
Fig. 1.1.13-b.1 Shortlisted Selection Line-UP (Second Level Form A) | 2018-05-24 | 2018-05-24
Fig. 1.1.13-b.2 Shortlisted Selection Line-UP (Second Level Form B) | 2018-05-24 | 2018-05-24
Plantilla of Casual Appointment |  |  |  | Done |  |  | Enhancement
Fig. 1.1.9 Plantilla of Casual Appointment (CS Form No. 34-F) | 2018-05-24 | 2018-05-24
Plantilla of Personnel Permanent |  |  |  | Done |  |  | Enhancement
Fig. 1.1.8-b Plantilla of Personnel (Permanent) | 2018-05-24 | 2018-05-24
Fig. 1.1.8-b Plantilla of Personnel (Permanent) -cont. | 2018-05-24 | 2018-05-24
Position Profiling |  |  |  | Done |  |  | Done
Fig. 1.1.17 Position Description Form (17 DBM-CSC-Form No.1) | 2019-05-22 | 2019-05-22
Rating Form |  |  |  | Done |  |  | Enhancement
Fig. 1.1.4-a.1 Rating Form for Applicants -1st Level – A1 | 2019-05-22 | 2019-05-22
Fig. 1.1.4-a.2 Rating Form for Applicants -1st Level – B2 | 2019-05-22 | 2019-05-22
Fig. 1.1.4-b.1 Rating Form for Applicants-2nd Level – A1 | 2019-05-22 | 2019-05-22
Fig. 1.1.4-b.2 Rating Form for Applicants-2nd Level – B2 | 2019-05-22 | 2019-05-22
Staffing Plan |  |  |  | Done |  |  | Enhancement
Fig. 1.1.15 Staffing Plan | 2019-05-23 | 2019-05-23
Vacant Position Entry |  |  |  | Done |  |  | Enhancement
Fig. 1.1.16 Recruitment Plan | 2019-05-21 | 2019-05-21
Fig. 1.1.6-a Request for Publication of Vacant Positions (CS Form No.9) | 2019-05-21 | 2019-05-21
Fig. 1.1.6-b.1 Request for Publication of Vacant Positions List | 2019-05-21 | 2019-05-21
Fig. 1.1.6-b.2 Request for Publication of Vacant Position Print List | 2019-05-21 | 2019-05-21
1.2 Performance Management |  |  | Elward |  |  | Gen
Consolidated Performance Rating Job-Order |  |  |  | Ongoing |  |  | Pending
Fig. 1.2.7 Consolidated Performance Rating – Job-Order | 2019-05-22 | 2019-05-22
Consolidated Performance Rating Permanent |  |  |  | Ongoing |  |  | Pending
Fig. 1.2.6 Consolidated Performance Rating – Permanent | 2019-05-22 | 2019-05-22
Driver’s Performance Evaluation |  |  |  | Ongoing |  |  | Pending
Fig. 1.2.5-a Driver’s Performance Evaluation Form | 2019-05-22 | 2019-05-22
Fig. 1.2.5-b Driver’s Performance Evaluation Form | 2019-05-22 | 2019-05-22
Fig. 1.2.5-c Driver’s Performance Evaluation Form | 2019-05-22 | 2019-05-22
Individual Performance Commitment and Review (IPCR) |  |  |  | Done |  |  | Enhancement
IPCR Core Function | 2019-05-20 | 2019-05-20
IPCR Success Indicator | 2019-05-20 | 2019-05-20
IPCR Actual Accomplishment | 2019-05-20 | 2019-05-20
Assign IPCR | 2019-05-20 | 2019-05-20
Fig. 1.2.2 IPCR with Work Target | 2019-05-20 | 2019-05-20
IPCR Result Monitoring | 2019-05-20 | 2019-05-20
OPCR Individual Ranking | 2019-05-20 | 2019-05-20
Office Performance Commitment and Review (OPCR) |  |  |  | Done |  |  | Ongoing
OPCR Core Function | 2019-05-21 | 2019-05-21 |  |  |  |  | Enhancement
OPCR Success Indicator | 2019-05-21 | 2019-05-21 |  |  |  |  | Enhancement
OPCR Actual Accomplishment | 2019-05-21 | 2019-05-21 |  |  |  |  | Enhancement
Assign OPCR | 2019-05-21 | 2019-05-21 |  |  |  |  | Enhancement
Fig. 1.2.1 OPCR with Work Target | 2019-05-21 | 2019-05-21 |  |  |  |  | Enhancement
OPCR Result Monitoring | 2019-05-21 | 2019-05-21 |  |  |  |  | Enhancement
OPCR Office Ranking | 2019-05-21 | 2019-05-21 |  |  |  |  | Enhancement
Performance Evaluation |  |  |  | Done |  |  | Enhancement
Fig. 1.2.4-a Performance Evaluation Form – Job Order | 2019-05-23 | 2019-05-23
Fig. 1.2.4-b Performance Evaluation Form – Job Order | 2019-05-23 | 2019-05-23
Fig. 1.2.4-c Performance Evaluation Form – Job Order | 2019-05-23 | 2019-05-23
Ranking by Department / Employee |  |  |  | Ongoing |  |  | Pending
Fig. 1.2.8 Ranking by Employee | 2019-05-23 | 2019-05-23
Fig. 1.2.8 Ranking by Department | 2019-05-23 | 2019-05-23
Rating Matrix |  |  |  | Ongoing |  |  | Pending
Fig. 1.2.3 -a Rating Matrix | 2019-05-24 | 2019-05-24
Fig. 1.2.3 -b Rating Matrix | 2019-05-24 | 2019-05-24
Fig. 1.2.3 -c Rating Matrix | 2019-05-24 | 2019-05-24
Rating Matrix Setup | 2019-05-24 | 2019-05-24
Rating Matrix Criteria | 2019-05-24 | 2019-05-24
1.3 Learning and Development |  |  | Joy |  |  | Joy/Joeann
Training Questionaire |  |  |  | Done |  |  | Enhancement
Fig. 1.3.1 Training Needs Questionnaire - Setup | 2019-05-20 | 2019-05-20
Training Questionaire Attachment | 2019-05-20 | 2019-05-20
Training Needs |  |  |  | Done |  |  | Enhancement
Fig. 1.3.2 Training Needs Analysis - Entry Form | 2019-05-20 | 2019-05-20
Training Annalysis Masterlist | 2019-05-20 | 2019-05-20
Training Course |  |  |  | Done |  |  | Enhancement
Training Course Setup
Training Course Outline
Individual Development Plan/Training Plan |  |  |  | Done |  |  | Enhancement
Fig. 1.3.3 Individual Development Plan/Training Plan | 2019-05-21 | 2019-05-21
Individual Development Plan Monitoring | 2019-05-21 | 2019-05-21
Attendance Monitoring |  |  |  | Done |  |  | Enhancement
Fig. 1.3.4 Training Attended/Monitoring | 2019-05-21 | 2019-05-21
Training Program Attendance List | 2019-05-21 | 2019-05-21
LGU-Naga, Cebu Internal University |  |  |  | Done |  |  | Enhancement
Fig. 1.3.5 List of Courses Attended | 2019-05-21 | 2019-05-21
Individual Courses Attended | 2019-05-21 | 2019-05-21
Departmental List Attended | 2019-05-21 | 2019-05-21
1.4 Rewards and Recognition
Birthday Greetings | 2019-05-22 | 2019-05-22 |  | Done |  |  | Enhancement
Comaparative Report (Chart) |  |  |  | Done |  |  | Enhancement
Fig. 1.4.9 -b Pie Chart -1 | 2019-05-23 | 2019-05-23 | Done | Done
Fig. 1.4.9 -b Pie Chart -2 | 2019-05-23 | 2019-05-23 | Done
Commendation |  |  |  | Ongoing |  |  | Pending
Fig. 1.4.4 Commendation (External Awards) | 2019-05-23 | 2019-05-23 | Gigil
Compensatory Time Off | 2019-05-22 | 2019-05-22 |  | Done |  |  | Enhancement
Fig. 1.4.12-a Compensatory Time Off (Annex A) | 2019-05-23 | 2019-05-23 | Done
Fig. 1.4.12-b.1 Summary/List of COC’s Issued and CTO’s Scheduled (Annex B) | 2019-05-24 | 2019-05-24 | Done
Fig. 1.4.12-b.2 Monthly Report on Compensatory Overtime Credits (COCs) (Annex C) | 2019-05-24 | 2019-05-24 | Done
Demographics of Awardees |  |  |  | Done |  |  | Enhancement
Fig. 1.4.14 Demographics of Awardees | 2019-05-24 | 2019-05-24 | Done
Leave Credits Monetize |  |  |  | Done |  |  | Enhancement
Fig. 1.4.11 Monetization of Leave Credits | 2019-05-24 | 2019-05-24 | Done By Josievel
Loyalty |  |  |  | Done |  |  | Done
Fig. 1.4.5 Loyalty | 2019-05-24 | 2019-05-24 | Done
Productivity Enhancement Incentive |  |  |  | Done |  |  | Enhancement
Fig. 1.4.10 Productivity Enhancement Incentive |  |  | Done
Reward and Recognition |  |  |  | Done |  |  | Enhancement
Fig. 1.4.1 Best Office | 2019-05-20 | 2019-05-20 | Gigil
Fig. 1.4.2 Best Employee |  |  | Gigil
Fig. 1.4.3 Perfect Attendance
Rewards and Recognition Budget Utilization |  |  |  | Done |  |  | Done
Fig. 1.4.15 Rewards and Recognition Budget Utilization – Link to Budget System | 2019-05-20 | 2019-05-20 | Done
Satisfactory Performance | 2019-05-20 | 2019-05-20 |  | Done |  |  | Done
Fig. 1.4.7 Mid-Year | 2019-05-20 | 2019-05-20 | Done
Fig. 1.4.8 Year-End | 2019-05-21 | 2019-05-21 | Done
Timeshift Setup/Change Timeshift | 2019-05-21 | 2019-05-21 |  | Done |  |  | Done
Years in Service | 2019-05-21 | 2019-05-21 |  | Done |  |  | Done
Fig. 1.4.6 Number of Years in Service | 2019-05-21 | 2019-05-21 | Done
1.5 Attendance -Timekeeping |  |  | Jayson
Batch DTR Entry | 2019-05-20 | 2019-05-20 |  | Done |  |  | Enhancement
Biometric Profiling | 2019-05-20 | 2019-05-20 |  | Done |  |  | Enhancement
Correction Time Log |  |  |  | Done | DTR Entry |  | Enhancement
Fig. 1.5.13 Correction of Time Log by Employee | 2019-05-21 | 2019-05-21
CTO Entry | 2019-05-21 | 2019-05-21 |  | Done |  |  | Enhancement
Daily Time Record |  |  |  | Done |  |  | Enhancement
Fig. 1.5.1-a CS Form No. 48 DTR Entry | 2019-05-22 | 2019-05-22
Fig. 1.5.1-b.1 CS Form No. 48 DTR List | 2019-05-22 | 2019-05-22
Fig. 1.5.1-b.2 CS Form No. 48 DTR Print | 2019-05-22 | 2019-05-22
Holiday Setup |  |  |  | Done |  |  | Enhancement
Fig. 1.5.12 Holiday Set-up | 2019-05-22 | 2019-05-22
Incident Report |  |  |  | Done |  |  | Enhancement
Fig. 1.5.2-a Incident Report – Form 1 | 2019-05-23 | 2019-05-23 |  |  | C/O To Sir ken
Fig. 1.5.2-b Incident Report – Form 2 | 2019-05-23 | 2019-05-23
Incomplete Logs | 2019-05-23 | 2019-05-23 |  | Done |  |  | Bugs
Official Business |  |  |  | Done |  |  | Enhancement
Fig. 1.5.4-c Application List Print | 2019-05-23 | 2019-05-23
Overtime Application |  |  |  | Ongoing |  |  | Enhancement
Fig. 1.5.10-a Overtime Application | 2019-05-24 | 2019-05-24
Fig. 1.5.10-b.1 Overtime Application List | 2019-05-24 | 2019-05-24
Fig. 1.5.10-b.2 Overtime Application Print List | 2019-05-24 | 2019-05-24
Fig. 1.5.10-b.3 Overtime Application Certification | 2019-05-24 | 2019-05-24
Fig. 1.5.10-b.4 Overtime Justification | 2019-05-24 | 2019-05-24
Pass Slip |  |  |  | Done |  |  | Enhancement
Fig. 1.5.4-a Pass Slip Entry | 2019-05-25 | 2019-05-25
Fig. 1.5.4-b Pass Slip List | 2019-05-25 | 2019-05-25
Fig. 1.5.4-d Individual Pass Slip/Time Adjustment Slip– front | 2019-05-25 | 2019-05-25
Fig. 1.5.4-e Individual Pass Slip/Time Adjustment Slip - back | 2019-05-25 | 2019-05-25
Timeshift Setup |  |  |  | Done |  |  | Enhancement
Fig. 1.5.11 Time Shift Schedule | 2019-05-25 | 2019-05-25
1.6 Leave Administration
Leave Application |  |  |  | Done |  |  | Enhancement
Fig. 1.6.2-a Application for Leave Form | 2019-05-20 | 2019-05-20 |  | done
Fig. 1.6.2-b.1 Application for Leave List | 2019-05-20 | 2019-05-20 |  | done
Fig. 1.6.2-b.2 Application for Leave Print List | 2019-05-20 | 2019-05-20 |  | done
Fig. 1.6.2-b.3 Application for Leave | 2019-05-20 | 2019-05-20 |  | done
Leave Approval |  |  |  | Done |  |  | Enhancement
Others | 2019-05-20 | 2019-05-20 |  | done
Leave Balance Summary Report |  |  |  | Done |  |  | Enhancement
Fig. 1.6.4 Leave Balance Summary Report | 2019-05-21 | 2019-05-21 |  | done
Leave Cancellation |  |  |  | Done |  |  | Enhancement
Others | 2019-05-21 | 2019-05-21 |  | done
Leave Credits/Beginning Balance Entry |  |  |  | Done |  |  | Enhancement
Others | 2019-05-21 | 2019-05-21 |  | done
Leave Ledger |  |  |  | Done |  |  | Enhancement
Fig. 1.6.3 Employee Leave Credits and Accumulation Report | 2019-05-21 | 2019-05-21 |  | done
Request for Absence |  |  |  | Done |  |  | Enhancement
Fig. 1.6.1 Request for Absence - Job-Order | 2019-05-21 | 2019-05-21 |  | done
1.7 Retirement and Other Personnel Services / Benefits
Agency Remittance |  |  |  | Done |  |  | Enhancement
Fig. 1.7.18-a Agency Remittance Advice Form A | 2019-05-22 | 2019-05-22 | done
Fig. 1.7.18-c Agency Remittance Advice Form C | 2019-05-22 | 2019-05-22 | done
Fig. 1.7.18-d Agency Remittance Advice Form D | 2019-05-22 | 2019-05-22 | done
Fig. 1.7.18-e Agency Remittance Advice Form E | 2019-05-22 | 2019-05-22 | done
Computation of Terminal Leave |  |  |  | Done |  |  | Enhancement
Department Profiling |  |  |  | Done |  |  | Enhancement
Drug Test Entry and Monitoring |  |  |  | Done |  |  | Enhancement
Employee Master List |  |  |  | Done |  |  | Enhancement
Employee Profiling |  |  |  | Done |  |  | Enhancement
Fig. 1.7.12-a Notice of Salary Adjustment | 2019-05-23 | 2019-05-23 | done
Fig. 1.7.12-c Notice of Step Increment | 2019-05-23 | 2019-05-23 | done
Fig. 1.7.19 Notice of Violations (TOP Type) | 2019-05-23 | 2019-05-23 | done/co jos
Fig. 1.7.4 Certification of Employment (Permanent/Casual & JO) | 2019-05-23 | 2019-05-23 | done
Fig. 1.7.5 Service Record Generic (Permanent & JO) | 2019-05-24 | 2019-05-24 | done
Fig. 1.7.6 Service Record GSIS | 2019-05-24 | 2019-05-24 | done
Fig. 1.7.7 Service Length | 2019-05-24 | 2019-05-24 | done
Fig. 1.7.8 Training Certificates | 2019-05-24 | 2019-05-24 | done
1.8 Complaints
Complaint Form |  |  |  | Done |  |  | Enhancement
Fig. 1.8.1.1 Complaint Form | 05/20/2019 | 05/20/2019 | Kenneth | Done |  | Gemalie | with concern
Fig. 1.8.1.3 Certification of Non-Forum Shopping | 05/21/2019 | 05/21/2019 | Kenneth | Done |  | Gemalie | with concern
Incident Report Form |  |  |  | Done |  |  | Enhancement
Fig. 1.8.1.2 Incident Report Form | 05/22/2019 | 05/22/2019 | Kenneth | Done |  | Gemalie | with concern
Minutes of the Meeting |  |  |  | Done |  |  | Ongoing
Fig. 1.8.1.4 Minutes of Meeting |  |  | c/o Brylle/Richard
Fig. 1.8.2.4 Minutes of Meeting |  |  | c/o Brylle/Richard
Fig. 1.8.2.5 Resolution/Decision |  |  | c/o Brylle/Richard
Resolution/Decision |  |  |  | Done |  |  | Enhancement
Fig. 1.8.1.5 Resolution/Decision |  |  | c/o Brylle/Richard
Grievance Form |  |  |  | Done |  |  | Enhancement
Fig. 1.8.2.1 Grievance Form | 05/23/2019 | 05/23/2019 | Kenneth | Done |  | Gemalie | with concern
Fig. 1.8.2.2 Grievance Agreement Form | 05/24/2019 | 05/24/2019 | Kenneth | Done |  | Gemalie | with concern
Fig. 1.8.2.3 Certificate of Final Action on the Grievance | 05/24/2019 | 05/24/2019 | Kenneth | Done |  | Gemalie | with concern
1.9 Citizens Charter
Charter | 2019-05-20 | 2019-05-20 |  | Done |  |  | Ongoing
1.10 General Settings |  |  | Jayson
LGU Name Setting | 2019-05-20 | 2019-05-20 |  | Done |  |  | Done
Department Setting | 2019-05-20 | 2019-05-20 |  | Done |  |  | Done
Elected Officials | 2019-05-20 | 2019-05-20 |  | Done |  |  | Done
Barangay Setting | 2019-05-20 | 2019-05-20 |  | Done |  |  | Enhancement
Header Settings | 2019-05-20 | 2019-05-20 |  | Done |  |  | Done
User Management | 2019-05-20 | 2019-05-20 |  | Done |  |  | Enhancement
1.10 Admistrative |  |  | Jayson
Holiday Setup |  |  |  | Done
Allowance Setup |  |  |  | Done
Appointment Status Setup |  |  |  | Done |  |  | Done
Deduction Setup |  |  |  | Done |  |  | Done
Department Setup |  |  |  | Done |  |  | Done
Employee Type |  |  |  | Done
JO Group |  |  |  | Done
Leave Setup |  |  |  | Done |  |  | Done
Pag-ibig setup |  |  |  | Done |  |  | Done
PhilHealth Setup |  |  |  | Done |  |  | Done
Payroll Group |  |  |  | Done
Position and Rate Setup |  |  |  | Done
Premium Setup |  |  |  | Done |  |  | Done
Salary Grade |  |  |  | Done
Time Shift |  |  |  | Done

## Bugs
Bugs Status | n
Modules | Bugs
1.1 Application | 21
1.2 Others | 38
1.3 Reports | 87
Grand Total | 146

## Enhancement
Enhancements | u
Modules | Enhancement
1.1 Application | 21
1.2 Others | 38
1.3 Reports | 87
Grand Total | 146

## Workload
[6 empty] | BASIC FUNCTIONALITY | [6 empty] | FORM DESIGN QA |  |  |  |  | REPORTDESIGN QA | [5 empty] | OVER ALL STATUS
Ready | Module | Forms/Activities | Owner | Start Date | End Date | C | R | U | D | T | P | E | FD | F | S | M | TT | HD | IM | FT | DT | CP | NF | Bugs | Enhancements | Comments
l | Business Tax | Fig 1.1.1.1-a (Business Assessment Form) | Peachie | 06-18-19 | 06-18-19 | [7 empty] | l | l | l | l | l | [6 empty] | l | l
l | Business Tax | Fig 1.1.1.1-b (Business Assessment) | Peachie | 06-18-19 | 06-18-19 | l | n | l | l | n | n | n | l | l | l | l | l | l | l | l | l | l | o | n | l
l | Business Tax | Fig 1.1.1.2-a Business Reassessment (Entry Form) | Peachie | [9 empty] | l | l | l | l | l | [6 empty] | l | l
l | Business Tax | Fig 1.1.1.2-b Business Reassessment | Peachie |  |  | l | l | l | l | l | l | l | l | l | l | l | l | l | l | l | l | l | o | l | l | with error. Please see screenshot
n | Business Tax | Copy Assessment | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
l | Business Tax | Fig 1.1.1.3 Business Payments | Peachie |  |  |  | n | o | o | l | l | l | l | l | l | l | o | l | l | o | o | o | o | n | l
l | Business Tax | Fig 1.1.1.4-a Business Payments History (Form) | Peachie |  |  | o | l | o | o | l | o | o | l | l | l | l | o | o | o | o | o | o |  | l | l | form: dili ma-open
l | Business Tax | Fig 1.1.1.4-b Business Payments History (Print-out) | Peachie |  |  | j | l | o | o | l | l | l | l | l | l | l | o | l | l | l | l | l |  | l | l | form: dili ma-open
n | Business Tax | Fig 1.1.1.5-a. Lot Occupant/Dwellers Entry Form | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
n | Business Tax | Fig 1.1.1.5-b. Lot Occupant/Dwellers List Form | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
n | Business Tax | Fig 1.1.1.5-c Lot Occupant/Dwellers Cashiering Form | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
n | Business Tax | Lot Occupant/Dwellers Ledger | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
n | Business Tax | Fig 1.1.1.5-d. Subsidiary Ledger per Lot Occupant/Dwellers | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
n | Business Tax | Fig 1.1.1.5-e. Subsidiary Ledger per Business | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
l | Business Tax | Fig 1.1.1.6-a Business Tax Delinquency | Peachie |  |  | o | l | o | o | l | l | o | l | l | l | l | o | l | l | l | l | l |  | l | l
l | Business Tax | Fig 1.1.1.6-b Notice of Delinquency | Peachie |  |  | l | l | o | o | l | l | o | l | l | l | l | o | l | l | n | n | n |  | n | l
l | Business Tax | Fig. 1.1.1.13 Business Delinquency Master List | Peachie |  |  | o | l | o | o | l | l | o | l | l | l | l | o | l | l | l | l | l | o | l | l
l | Business Tax | Fig. 1.1.1.7- a New/Renew/Retired Business Form | Peachie |  |  | lo | o | o | o | o | o | o | l | l | l | l | l | o | o | o | o | o |  | l | l
l | Business Tax | Fig. 1.1.1.7-b New/Renew/Retired Business Reports | Peachie |  |  |  | l | o | o | l | l | l | l | l | l | l | l | l | l | l | l | l |  | l | l
l | Business Tax | Fig. 1.1.1.8 Business Tax Payment Certificate | Peachie |  |  | o | l | o | o | l | l | l | l | l | l | l | l | l | l | n | n | n |  | n | l
l | Business Tax | Fig 1.1.1.9-a Rental Notice of Delinquency (First notice) | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
l | Business Tax | Fig 1.1.1.9-b Notice of Delinquency (Second notice) | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
l | Business Tax | Fig 1.1.1.9-c Notice of Delinquency (Final / Padlock Notice) | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
n | Business Tax | Tax Credit Entry | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
n | Business Tax | Fig 1.1.1.11 Record of Tax Credit | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
l | Business Tax | Fig. 1.1.1.12 on SEF/GF/TF Report | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
l | Business Tax | Fig. 1.1.1.13 Business Delinquency Master List | Peachie |  |  |  | l | o | o | l | l | o | l | l | l | l | o | l | l | l | l | l |  | l | l
l | Business Tax | List of New Business | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | o | l | l
l | Business Tax | List of ReNew Business | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | o | l | l
l | Business Tax | List of Terminated Business | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | o | l | l
l | Business Tax | Fig. 1.1.1.14 Business Tax Certification on Closure | Peachie |  |  |  | l | o | o | l | l | o | l | l | l | l | o | l | l | l | l | l | o | l | l
n | Business Tax | Fig. 1.1.1.15 a -Franchise Tax | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
n | Business Tax | Fig. 1.1.1.15 b -Franchise Tax -Subsidiary ledger of Foreshore | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
n | Business Tax | Fig. 1.1.1.15 c -Franchise Tax -Statement of Account | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | o | l | l
n | Business Tax | Foreshore Cashiering (Direct to Cashbook) | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
n | Business Tax | Foreshore Ledger | Peachie |  |  | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q | q |  | l | l
l | Business Tax | Fig. 1.1.1.16 Business Collectables | Peachie |  |  |  | l | o | o | l | l | l | l | l | l | l | o | o | l | l | l | l |  | l | l
l | Business Tax | Previous | Peachie |  |  |  | l | o | o | l | l | l | l | l | l | l | o | o | l | l | l | l |  | l | l
l | Business Tax | Current | Peachie |  |  |  | l | o | o | l | l | l | l | l | l | l | o | o | l | l | l | l |  | l | l
l | Business Tax | Comparative | Peachie |  |  |  | l | o | o | l | l | l | l | l | l | l | o | o | l | l | l | l | o | l | l
l | General Collection | Fig. 1.1.1.14 Business Tax Certification on Closure | Peachie |  |  | o | l | o | o | l | l | l | l | l | l | l | lo | l | l | l | l | l | o | l | l
l |  | Fig. 1.1.1.16 Business Collectables |  |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | Previous | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l |  | Current | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | Comparative | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | Fig 1.1.1.5-a. Lot Occupant/Dwellers Entry Form | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | Fig 1.1.1.5-b. Lot Occupant/Dwellers List Form | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | Lot Occupant/Dwellers Ledger | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l |  | Fig 1.1.1.5-c Lot Occupant/Dwellers Cashiering Form | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig 1.1.1.5-d. Subsidiary Ledger per Lot Occupant/Dwellers | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig 1.1.1.5-e. Subsidiary Ledger per Business | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig 1.1.1.11 Record Tax Credit | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.1.1.15 a -Franchise Tax | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.1.1.15 b -Foreshore -Subsidiary ledger of Fore Share Entry | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.1.1.15 c -Foreshore -Statement of Account | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Foreshore Cashiering (Direct to Cashbook) | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Foreshore Ledger | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.16 (Permit Status Report) | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.17 (Kind of Business) | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.18 (Tax Payer Report) | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.19 (DTI Report) | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.1 Business Application Notice of Violation | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.2 Business Application Notice of Closure | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.3 Business Application Termination | GEN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | [5 empty] | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | 1.1.2 Transfer - Location | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l |  | Business Master List | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | 1.1.3 Issuance of Business Permit | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | 1.1.4 Customer Inquiry | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.4 Fire Clearance | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.5 BFP Negative Listing | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l |  | Transferred Business List | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.4 (Released Business Permits) | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.5 (Business Information Report) | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.6 (Business History) | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.9 (SME Report) | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.10 (LGU Quarterly Progress Report) | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.11 (BSP Report) | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.12 (Consolidation and Retrieval of Negative or Positive Findings) | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.15 (DILG Monitoring Report) | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.16 (Permit Status Report) | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.17 (Kind of Business) | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.18 (Tax Payer Report) | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.19 (DTI Report) | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.1 Business Application Notice of Violation | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.2 Business Application Notice of Closure | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.3 Business Application Termination | NINO |  |  | n | [6 empty] | u | [10 empty] | n | u
l | [5 empty] | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | 1.1.2 Business Amendment | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l |  | Business Master List | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | 1.1.3 Issuance of Business Permit | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | 1.1.4 Customer Inquiry | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.4 Fire Clearance | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.5 BFP Negative Listing | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l |  | Amended Business List | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.4 (Released Business Permits) | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.5 (Business Information Report) | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.6 (Business History) | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.9 (SME Report) | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.10 (LGU Quarterly Progress Report) | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.11 (BSP Report) | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.12 (Consolidation and Retrieval of Negative or Positive Findings) | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.15 (DILG Monitoring Report) | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.16 (Permit Status Report) | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.17 (Kind of Business) | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.18 (Tax Payer Report) | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.19 (DTI Report) | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.1 Business Application Notice of Violation | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.2 Business Application Notice of Closure | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.3 Business Application Termination | JOEANN |  |  | n | [6 empty] | u | [10 empty] | n | u
l | [5 empty] | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | 1.1.2 Business One-Stop-Shop | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l |  | Business Master List | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | 1.1.3 Issuance of Business Permit | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | 1.1.4 Customer Inquiry | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.4 Fire Clearance | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.5 BFP Negative Listing | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.1 (New Business List) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.2 (Renewed Business List) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.3 (Unrenewed Business List) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.4 (Released Business Permits) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.5 (Business Information Report) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.9 (SME Report) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.10 (LGU Quarterly Progress Report) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.11 (BSP Report) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.12 (Consolidation and Retrieval of Negative or Positive Findings) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.15 (DILG Monitoring Report) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.16 (Permit Status Report) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.17 (Kind of Business) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.18 (Tax Payer Report) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.19 (DTI Report) | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.1 Business Application Notice of Violation | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.2 Business Application Notice of Closure | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.3 Business Application Termination | DIOCRES |  |  | n | [6 empty] | u | [10 empty] | n | u
l | [5 empty] | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | 1.1.5 Conditional Permit | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l |  | Business Master List | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | 1.1.3 Issuance of Business Permit | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.1 Application | 1.1.4 Customer Inquiry | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.4 Fire Clearance | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.5 BFP Negative Listing | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.8 (Conditional Business List) | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.5 (Business Information Report) | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.9 (SME Report) | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.10 (LGU Quarterly Progress Report) | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.11 (BSP Report) | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.12 (Consolidation and Retrieval of Negative or Positive Findings) | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.15 (DILG Monitoring Report) | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.16 (Permit Status Report) | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.17 (Kind of Business) | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.18 (Tax Payer Report) | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.3 Reports | Fig. 1.3.19 (DTI Report) | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.1 Business Application Notice of Violation | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.2 Business Application Notice of Closure | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.3 Business Application Termination | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.6 Trisikad Permit | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.7 Tricycle Permit | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
l | 1.2 Others | 1.2.8 Assorted Permit | BRYLLE |  |  | n | [6 empty] | u | [10 empty] | n | u
[6 empty] | l | l | Pass | [5 empty] | E | Export
[6 empty] | n | n | Error | [5 empty] | FD | Form Design
[6 empty] | u | u | Enhancement | [5 empty] | M | Masking
[6 empty] | q | q | Not Started | [5 empty] | F | Font
[6 empty] | p | o | Not Applicable | [5 empty] | S | Spelling
[6 empty] | h | h | Fo Clarification | [5 empty] | TT | TootTip
[6 empty] | . | . | Start | [5 empty] | HD | Header
[6 empty] | .. | .. | Change Sched | [5 empty] | IM | Indents / Margin
[6 empty] | x | x | End of Execution | [5 empty] | FT | Footer
[6 empty] | w | w | [6 empty] | DT | Date & Time Stamp
[14 empty] | CP | Copyright
[14 empty] | NF | National Form Templates
Note on H4: ADMIN: Record Count: Fail
Note on K4: ADMIN: trapping for the column search
Note on L4: ADMIN: See screenshot for the details
Note on J6: ADMIN: with error; please see screenshot
Note on K6: ADMIN: with error; please see screenshot
Note on H8: ADMIN: Please adjust ang display sa screen. Please see screenshot
Note on U18: ADMIN: please see screenshot
Note on U22: ADMIN: no ft
Note on V22: ADMIN: no DT
Note on W22: ADMIN: no CP

## Screenshot
Business Account No.
Approval Recommended By:

## Scope (hidden)
Sub Module | Type | Figure No | Form/Report Name | Owner | Assigned Date | Completion Date
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.1 Personal Data Sheet Entry Form (Basic Info) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.2 Personal Data Sheet Entry Form (Family Background) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.3 Personal Data Sheet Entry Form (Educational Background) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.4 Personal Data Sheet Entry Form (Civil Service Eligibility) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.5 Personal Data Sheet Entry Form (Work Experience) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.6 Personal Data Sheet Entry Form (Voluntary Work) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.7 Personal Data Sheet Entry Form (Training Programs) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.8 Personal Data Sheet Entry Form (Other Information) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.9 Personal Data Sheet Entry Form (Other Information) Cont. | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.10 Personal Data Sheet Entry Form (References) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.11 Personal Data Sheet Entry Form (Employment Information) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.12 Leave Type | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-b.1 Personal Data Sheet (CS Form No.212) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-b.2 Personal Data Sheet (CS Form No.212) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-b.3 Personal Data Sheet (CS Form No.212) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-b.4 Personal Data Sheet (CS Form No.212) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.2-a.1 Certificate of Appointment (CS Form No.33B) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.2-a.2 Certificate of Appointment (CS Form No.33B) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.3 Manpower Request/Reassignment | Manpower Request/Reassignment | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.4-a.1 Rating Form for Applicants -1st Level – A1 | Rating Form | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.4-a.2 Rating Form for Applicants -1st Level – B2 | Rating Form | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.4-b.1 Rating Form for Applicants-2nd Level – A1 | Rating Form | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.4-b.2 Rating Form for Applicants-2nd Level – B2 | Rating Form | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.5-a.1 Appointment Processing Checklist | Applicants Entry | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.5-a.2 Appointment Processing Checklist | Applicants Entry | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.6-a Request for Publication of Vacant Positions (CS Form No.9) | Vacant Position Entry | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.6-b.1 Request for Publication of Vacant Positions List | Vacant Position Entry | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.6-b.2 Request for Publication of Vacant Position Print List | Vacant Position Entry | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.7 Notices | Applicants Entry | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.8-b Plantilla of Personnel (Permanent) | Plantilla of Personnel Permanent | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.8-b Plantilla of Personnel (Permanent) -cont. | Plantilla of Personnel Permanent | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.9 Plantilla of Casual Appointment (CS Form No. 34-F) | Plantilla of Casual Appointment | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.10 Personnel Schedule – Per Office | Personnel Scheduler | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.11 Personnel Schedule - Consolidated | Personnel Scheduler | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.12 Manpower Request Summary | Manpower Request Summary | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.13-a.1 Shortlisted Selection Line-UP (First Level Form A) | Personnel Scheduler | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.13-a.2 Shortlisted Selection Line-UP (First Level Form B) | Personnel Scheduler | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.13-b.1 Shortlisted Selection Line-UP (Second Level Form A) | Personnel Scheduler | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.13-b.2 Shortlisted Selection Line-UP (Second Level Form B) | Personnel Scheduler | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.13-c Comparative Assessment | Comparative Assessment | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.14-a Applicant Profile Form | Applicants Entry | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.14-b.1 Applicant Entry List | Applicants Entry | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.14-b.2 Applicant Print List | Applicants Entry | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.15 Staffing Plan | Staffing Plan | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.16 Recruitment Plan | Vacant Position Entry | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.17 Position Description Form (17 DBM-CSC-Form No.1) | Position Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.18 Appointment Transmittal and Action Form (CS Form No.1)/RAI | Appoinment Transmittal | Gilbert
1.2 Performance Management | Forms | Fig. 1.2.1 Office Performance Commitment and Review (OPCR) with Work Target | Office Performance Commitment and Review (OPCR) | Elward
1.2 Performance Management | Forms | Fig. 1.2.2 Individual Performance Commitment and Review (IPCR) with Work Target | Individual Performance Commitment and Review (IPCR) | Elward
1.2 Performance Management | Forms | Fig. 1.2.3 -a Rating Matrix | Rating Matrix | Elward
1.2 Performance Management | Forms | Fig. 1.2.3 -b Rating Matrix | Rating Matrix | Elward
1.2 Performance Management | Forms | Fig. 1.2.3 -c Rating Matrix | Rating Matrix | Elward
1.2 Performance Management | Forms | Fig. 1.2.4-a Performance Evaluation Form – Job Order | Performance Evaluation | Elward
1.2 Performance Management | Forms | Fig. 1.2.4-b Performance Evaluation Form – Job Order | Performance Evaluation | Elward
1.2 Performance Management | Forms | Fig. 1.2.4-c Performance Evaluation Form – Job Order | Performance Evaluation | Elward
1.2 Performance Management | Forms | Fig. 1.2.5-a Driver’s Performance Evaluation Form | Driver’s Performance Evaluation | Elward
1.2 Performance Management | Forms | Fig. 1.2.5-b Driver’s Performance Evaluation Form | Driver’s Performance Evaluation | Elward
1.2 Performance Management | Forms | Fig. 1.2.5-c Driver’s Performance Evaluation Form | Driver’s Performance Evaluation | Elward
1.2 Performance Management | Reports | Fig. 1.2.6 Consolidated Performance Rating – Permanent | Consolidated Performance Rating Permanent | Elward
1.2 Performance Management | Reports | Fig. 1.2.7 Consolidated Performance Rating – Job-Order | Consolidated Performance Rating Job-Order | Elward
1.2 Performance Management | Reports | Fig. 1.2.8 Ranking by Department / Employee | Ranking by Department / Employee | Elward
1.3 Learning and Development | Forms | Fig. 1.3.1 Training Needs Questionnaire – No Form | Questionaire Setup | Joy
1.3 Learning and Development | Forms | Fig. 1.3.2 Training Needs Analysis - No Form | Training Needs Questionaire/Training Needs Analysis | Joy
1.3 Learning and Development | Forms | Fig. 1.3.3 Individual Development Plan/Training Plan | Individual Development Plan/Training Plan | Joy
1.3 Learning and Development | Forms | Fig. 1.3.4 Training Attended/Monitoring | Training Attendance Monitoring | Joy
1.3 Learning and Development | Forms | Fig. 1.3.5 LGU-Naga, Cebu Internal University | Internal University | Joy
1.3 Learning and Development | Forms | Others | Questionaire Setup | Joy
1.3 Learning and Development | Forms | Others | Training Course Setup | Joy
1.4 Rewards and Recognition | Forms | Fig. 1.4.1 Best Office | Reward and Recognition | MJ
1.4 Rewards and Recognition | Forms | Fig. 1.4.2 Best Employee | Reward and Recognition | MJ
1.4 Rewards and Recognition | Forms | Fig. 1.4.3 Perfect Attendance | Reward and Recognition | MJ
1.4 Rewards and Recognition | Forms | Fig. 1.4.4 Commendation (External Awards) | Commendation | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.5 Loyalty | Loyalty | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.6 Number of Years in Service | Years in Service | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.7 Mid-Year | Satisfactory Performance | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.8 Year-End | Satisfactory Performance | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.9 -b Pie Chart -1 | Comaparative Report (Chart) | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.9 -b Pie Chart -2 | Comaparative Report (Chart) | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.10 Productivity Enhancement Incentive | Productivity Enhancement Incentive | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.11 Monetization of Leave Credits | Leave Credits Monetize | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.12-a Compensatory Time Off (Annex A) | Compensatory Time Off | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.12-b.1 Summary/List of COC’s Issued and CTO’s Scheduled (Annex B) | Compensatory Time Off | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.12-b.2 Monthly Report on Compensatory Overtime Credits (COCs) (Annex C) | Compensatory Time Off | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.13 Flexi-Time | Timeshift Setup/Change Timeshift | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.14 Demographics of Awardees | Demographics of Awardees | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.15 Rewards and Recognition Budget Utilization – Link to Budget System | Rewards and Recognition Budget Utilization | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.16 Birthday Greetings | Birthday Greetings | MJ
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.1-a CS Form No. 48 DTR Entry | Daily Time Record | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.1-b.1 CS Form No. 48 DTR List | Daily Time Record | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.1-b.2 CS Form No. 48 DTR Print | Daily Time Record | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.2-a Incident Report – Form 1 | Incident Report | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.2-b Incident Report – Form 2 | Incident Report | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.3 Travel Order | Travel Order | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.4-a Pass Slip Entry | Pass Slip | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.4-b Pass Slip List | Pass Slip | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.4-c Application List Print | Official Business | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.4-d Individual Pass Slip/Time Adjustment Slip– front | Pass Slip | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.4-e Individual Pass Slip/Time Adjustment Slip - back | Pass Slip | Jayson
1.5 Attendance -Timekeeping | Report | Fig. 1.5.5 Travel Abroad | Travel Order Report | Jayson
1.5 Attendance -Timekeeping | Report | Fig. 1.5.6 Punctuality Report and Frequency | Punctuality Report and Frequency | Jayson
1.5 Attendance -Timekeeping | Report | Fig. 1.5.7 Perfect Attendance | Perfect Attendance | Jayson
1.5 Attendance -Timekeeping | Report | Fig. 1.5.8 Notification of Tardiness to Department/Office Heads | Notice of Tardiness | Jayson
1.5 Attendance -Timekeeping | Report | Fig. 1.5.9 Flag Ceremony/Retreat/Mandatory Events - Attendance Monitoring | Att | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.10-a Overtime Application | Overtime Application | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.10-b.1 Overtime Application List | Overtime Application | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.10-b.2 Overtime Application Print List | Overtime Application | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.10-b.3 Overtime Application Certification | Overtime Application | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.10-b.4 Overtime Justification | Overtime Application | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.11 Time Shift Schedule | Timeshift Setup | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.12 Holiday Set-up | Holiday Setup | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.13 Correction of Time Log by Employee | Correction Time Log | Jayson
1.5 Attendance -Timekeeping | Forms | Others | Biometric Profiling | Jayson
1.5 Attendance -Timekeeping | Forms | Others | Incomplete Logs | Jayson
1.5 Attendance -Timekeeping | Forms | Others | Batch DTR Entry | Jayson
1.5 Attendance -Timekeeping | Forms | Others | CTO Entry | Jayson
1.6 Leave Administration | Forms | Fig. 1.6.1 Request for Absence - Job-Order | Request for Absence | Richard
1.6 Leave Administration | Forms | Fig. 1.6.2-a Application for Leave Form | Leave Application | Richard
1.6 Leave Administration | Forms | Fig. 1.6.2-b.1 Application for Leave List | Leave Application | Richard
1.6 Leave Administration | Forms | Fig. 1.6.2-b.2 Application for Leave Print List | Leave Application | Richard
1.6 Leave Administration | Forms | Fig. 1.6.2-b.3 Application for Leave | Leave Application | Richard
1.6 Leave Administration | Reports | Fig. 1.6.3 Employee Leave Credits and Accumulation Report | Leave Ledger | Richard
1.6 Leave Administration | Reports | Fig. 1.6.4 Leave Balance Summary Report | Leave Balance Summary Report | Richard
1.6 Leave Administration | Forms | Others | Leave Approval | Richard
1.6 Leave Administration | Forms | Others | Leave Cancellation | Richard
1.6 Leave Administration | Forms | Others | Leave Credits/Beginning Balance Entry | Richard
1.7 Retirement and Other Personnel Services / Benefits | Forms | Fig. 1.7.1-a Approval & Acceptance of Retirement or Resignation | Retirement and Separation
1.7 Retirement and Other Personnel Services / Benefits | Forms | Fig. 1.7.1-b Clearance (Resignation/Retirement) | Retirement and Separation
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.2 Evaluation Worksheet on Accumulated Leave Credits | Evaluation Worksheet
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.3 Computation of Terminal Leave | Computation of Terminal Leave
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.4 Certification of Employment (Permanent/Casual & JO) | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.5 Service Record Generic (Permanent & JO) | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.6 Service Record GSIS | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.7 Service Length | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.8 Training Certificates | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.9 Increment List / Schedule | Inrement Schedule
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.10 Loyalty List/Schedule | Loyalty List
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.11 Step Increment List | Step Increment List
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.12-a Notice of Salary Adjustment | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.12-b Salary Adjustment Report | Salary Adjustment Report
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.12-c Notice of Step Increment | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.13 Employee Summary Count | Employee Summary Count
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.14 Employee Master List | Employee Master List
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.15 Department/Office List | Department Profiling
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.16 Memo’s and Violations | Memos and Violations
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.17 -a Memo’s Offenses Set (2017 RACCS) | Memos and Violations
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.17 -b Memo’s Offenses Set (2017 RACCS) | Memos and Violations
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.17 -c Memo’s Offenses Set (2017 RACCS) | Memos and Violations
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.17 -d Memo’s Offenses Set (2017 RACCS) | Memos and Violations
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.18-a Agency Remittance Advice Form A | Agency Remittance
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.18-c Agency Remittance Advice Form C | Agency Remittance
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.18-d Agency Remittance Advice Form D | Agency Remittance
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.18-e Agency Remittance Advice Form E | Agency Remittance
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.19 Notice of Violations (TOP Type) | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.20 ID Generation | ID Generation
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.21 Organizational & Functional Chart | Organizational & Functional Chart
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.22 Drug Test Tagging and Monitoring | Drug Test Entry and Monitoring
1.8 Complaints |  | Fig. 1.8.1.1 Complaint Form | Complaint Form
1.8 Complaints |  | Fig. 1.8.1.2 Incident Report Form | Incident Report Form
1.8 Complaints |  | Fig. 1.8.1.3 Certification of Non-Forum Shopping | Complaint Form
1.8 Complaints |  | Fig. 1.8.1.4 Minutes of Meeting | Minutes of the Meeting
1.8 Complaints |  | Fig. 1.8.1.5 Resolution/Decision | Resolution/Decision
1.8 Complaints |  | Fig. 1.8.2.1 Grievance Form | Grievance Form
1.8 Complaints |  | Fig. 1.8.2.2 Grievance Agreement Form | Grievance Form
1.8 Complaints |  | Fig. 1.8.2.3 Certificate of Final Action on the Grievance | Grievance Form
1.8 Complaints |  | Fig. 1.8.2.4 Minutes of Meeting | Minutes of the Meeting
1.8 Complaints |  | Fig. 1.8.2.5 Resolution/Decision | Minutes of the Meeting
1.9 Citizen’s Charter |  | Fig. 1.9.1-a Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-b Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-c Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-d Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-e Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-f Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-g Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-h Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-i Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-j Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-k Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-l Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-m Citizen’s Charter | Citizen’s Charter
1.10 General Settings |  | LGU Name Setting | LGU Name Setting
1.10 General Settings |  | Department Setting | Department Setting
1.10 General Settings |  | Elected Officials | Elected Officials
1.10 General Settings |  | Barangay Setting | Barangay Setting
1.10 General Settings |  | Header Setiings | Header Setiings

## Scope (2) (hidden)
Sub Module | Type | Figure No | Form/Report Name | Owner | Assigned Date | Completion Date
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.1 Personal Data Sheet Entry Form (Basic Info) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.2 Personal Data Sheet Entry Form (Family Background) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.3 Personal Data Sheet Entry Form (Educational Background) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.4 Personal Data Sheet Entry Form (Civil Service Eligibility) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.5 Personal Data Sheet Entry Form (Work Experience) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.6 Personal Data Sheet Entry Form (Voluntary Work) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.7 Personal Data Sheet Entry Form (Training Programs) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.8 Personal Data Sheet Entry Form (Other Information) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.9 Personal Data Sheet Entry Form (Other Information) Cont. | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.10 Personal Data Sheet Entry Form (References) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.11 Personal Data Sheet Entry Form (Employment Information) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-a.12 Leave Type | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-b.1 Personal Data Sheet (CS Form No.212) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-b.2 Personal Data Sheet (CS Form No.212) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-b.3 Personal Data Sheet (CS Form No.212) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.1-b.4 Personal Data Sheet (CS Form No.212) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.2-a.1 Certificate of Appointment (CS Form No.33B) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.2-a.2 Certificate of Appointment (CS Form No.33B) | Employee Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.3 Manpower Request/Reassignment | Manpower Request/Reassignment | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.4-a.1 Rating Form for Applicants -1st Level – A1 | Rating Form | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.4-a.2 Rating Form for Applicants -1st Level – B2 | Rating Form | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.4-b.1 Rating Form for Applicants-2nd Level – A1 | Rating Form | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.4-b.2 Rating Form for Applicants-2nd Level – B2 | Rating Form | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.5-a.1 Appointment Processing Checklist | Applicants Entry | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.5-a.2 Appointment Processing Checklist | Applicants Entry | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.6-a Request for Publication of Vacant Positions (CS Form No.9) | Vacant Position Entry | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.6-b.1 Request for Publication of Vacant Positions List | Vacant Position Entry | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.6-b.2 Request for Publication of Vacant Position Print List | Vacant Position Entry | Gilbert
1.1 Recruitment, Selection and Placement | Forms | Fig. 1.1.7 Notices | Applicants Entry | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.8-b Plantilla of Personnel (Permanent) | Plantilla of Personnel Permanent | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.8-b Plantilla of Personnel (Permanent) -cont. | Plantilla of Personnel Permanent | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.9 Plantilla of Casual Appointment (CS Form No. 34-F) | Plantilla of Casual Appointment | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.10 Personnel Schedule – Per Office | Personnel Scheduler | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.11 Personnel Schedule - Consolidated | Personnel Scheduler | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.12 Manpower Request Summary | Manpower Request Summary | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.13-a.1 Shortlisted Selection Line-UP (First Level Form A) | Personnel Scheduler | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.13-a.2 Shortlisted Selection Line-UP (First Level Form B) | Personnel Scheduler | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.13-b.1 Shortlisted Selection Line-UP (Second Level Form A) | Personnel Scheduler | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.13-b.2 Shortlisted Selection Line-UP (Second Level Form B) | Personnel Scheduler | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.13-c Comparative Assessment | Comparative Assessment | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.14-a Applicant Profile Form | Applicants Entry | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.14-b.1 Applicant Entry List | Applicants Entry | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.14-b.2 Applicant Print List | Applicants Entry | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.15 Staffing Plan | Staffing Plan | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.16 Recruitment Plan | Vacant Position Entry | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.17 Position Description Form (17 DBM-CSC-Form No.1) | Position Profiling | Gilbert
1.1 Recruitment, Selection and Placement | Reports | Fig. 1.1.18 Appointment Transmittal and Action Form (CS Form No.1)/RAI | Appoinment Transmittal | Gilbert
1.2 Performance Management | Forms | Fig. 1.2.1 Office Performance Commitment and Review (OPCR) with Work Target | Office Performance Commitment and Review (OPCR) | Elward
1.2 Performance Management | Forms | Fig. 1.2.2 Individual Performance Commitment and Review (IPCR) with Work Target | Individual Performance Commitment and Review (IPCR) | Elward
1.2 Performance Management | Forms | Fig. 1.2.3 -a Rating Matrix | Rating Matrix | Elward
1.2 Performance Management | Forms | Fig. 1.2.3 -b Rating Matrix | Rating Matrix | Elward
1.2 Performance Management | Forms | Fig. 1.2.3 -c Rating Matrix | Rating Matrix | Elward
1.2 Performance Management | Forms | Fig. 1.2.4-a Performance Evaluation Form – Job Order | Performance Evaluation | Elward
1.2 Performance Management | Forms | Fig. 1.2.4-b Performance Evaluation Form – Job Order | Performance Evaluation | Elward
1.2 Performance Management | Forms | Fig. 1.2.4-c Performance Evaluation Form – Job Order | Performance Evaluation | Elward
1.2 Performance Management | Forms | Fig. 1.2.5-a Driver’s Performance Evaluation Form | Driver’s Performance Evaluation | Elward
1.2 Performance Management | Forms | Fig. 1.2.5-b Driver’s Performance Evaluation Form | Driver’s Performance Evaluation | Elward
1.2 Performance Management | Forms | Fig. 1.2.5-c Driver’s Performance Evaluation Form | Driver’s Performance Evaluation | Elward
1.2 Performance Management | Reports | Fig. 1.2.6 Consolidated Performance Rating – Permanent | Consolidated Performance Rating Permanent | Elward
1.2 Performance Management | Reports | Fig. 1.2.7 Consolidated Performance Rating – Job-Order | Consolidated Performance Rating Job-Order | Elward
1.2 Performance Management | Reports | Fig. 1.2.8 Ranking by Department / Employee | Ranking by Department / Employee | Elward
1.3 Learning and Development | Forms | Fig. 1.3.1 Training Needs Questionnaire – No Form | Questionaire Setup | Joy
1.3 Learning and Development | Forms | Fig. 1.3.2 Training Needs Analysis - No Form | Training Needs Questionaire/Training Needs Analysis | Joy
1.3 Learning and Development | Forms | Fig. 1.3.3 Individual Development Plan/Training Plan | Individual Development Plan/Training Plan | Joy
1.3 Learning and Development | Forms | Fig. 1.3.4 Training Attended/Monitoring | Training Attendance Monitoring | Joy
1.3 Learning and Development | Forms | Fig. 1.3.5 LGU-Naga, Cebu Internal University | Internal University | Joy
1.3 Learning and Development | Forms | Others | Questionaire Setup | Joy
1.3 Learning and Development | Forms | Others | Training Course Setup | Joy
1.4 Rewards and Recognition | Forms | Fig. 1.4.1 Best Office | Reward and Recognition | MJ
1.4 Rewards and Recognition | Forms | Fig. 1.4.2 Best Employee | Reward and Recognition | MJ
1.4 Rewards and Recognition | Forms | Fig. 1.4.3 Perfect Attendance | Reward and Recognition | MJ
1.4 Rewards and Recognition | Forms | Fig. 1.4.4 Commendation (External Awards) | Commendation | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.5 Loyalty | Loyalty | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.6 Number of Years in Service | Years in Service | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.7 Mid-Year | Satisfactory Performance | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.8 Year-End | Satisfactory Performance | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.9 -b Pie Chart -1 | Comaparative Report (Chart) | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.9 -b Pie Chart -2 | Comaparative Report (Chart) | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.10 Productivity Enhancement Incentive | Productivity Enhancement Incentive | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.11 Monetization of Leave Credits | Leave Credits Monetize | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.12-a Compensatory Time Off (Annex A) | Compensatory Time Off | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.12-b.1 Summary/List of COC’s Issued and CTO’s Scheduled (Annex B) | Compensatory Time Off | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.12-b.2 Monthly Report on Compensatory Overtime Credits (COCs) (Annex C) | Compensatory Time Off | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.13 Flexi-Time | Timeshift Setup/Change Timeshift | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.14 Demographics of Awardees | Demographics of Awardees | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.15 Rewards and Recognition Budget Utilization – Link to Budget System | Rewards and Recognition Budget Utilization | MJ
1.4 Rewards and Recognition | Report | Fig. 1.4.16 Birthday Greetings | Birthday Greetings | MJ
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.1-a CS Form No. 48 DTR Entry | Daily Time Record | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.1-b.1 CS Form No. 48 DTR List | Daily Time Record | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.1-b.2 CS Form No. 48 DTR Print | Daily Time Record | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.2-a Incident Report – Form 1 | Incident Report | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.2-b Incident Report – Form 2 | Incident Report | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.3 Travel Order | Travel Order | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.4-a Pass Slip Entry | Pass Slip | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.4-b Pass Slip List | Pass Slip | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.4-c Application List Print | Official Business | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.4-d Individual Pass Slip/Time Adjustment Slip– front | Pass Slip | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.4-e Individual Pass Slip/Time Adjustment Slip - back | Pass Slip | Jayson
1.5 Attendance -Timekeeping | Report | Fig. 1.5.5 Travel Abroad | Travel Order Report | Jayson
1.5 Attendance -Timekeeping | Report | Fig. 1.5.6 Punctuality Report and Frequency | Punctuality Report and Frequency | Jayson
1.5 Attendance -Timekeeping | Report | Fig. 1.5.7 Perfect Attendance | Perfect Attendance | Jayson
1.5 Attendance -Timekeeping | Report | Fig. 1.5.8 Notification of Tardiness to Department/Office Heads | Notice of Tardiness | Jayson
1.5 Attendance -Timekeeping | Report | Fig. 1.5.9 Flag Ceremony/Retreat/Mandatory Events - Attendance Monitoring |  | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.10-a Overtime Application | Overtime Application | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.10-b.1 Overtime Application List | Overtime Application | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.10-b.2 Overtime Application Print List | Overtime Application | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.10-b.3 Overtime Application Certification | Overtime Application | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.10-b.4 Overtime Justification | Overtime Application | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.11 Time Shift Schedule | Timeshift Setup | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.12 Holiday Set-up | Holiday Setup | Jayson
1.5 Attendance -Timekeeping | Forms | Fig. 1.5.13 Correction of Time Log by Employee | Correction Time Log | Jayson
1.5 Attendance -Timekeeping | Forms | Others | Biometric Profiling | Jayson
1.5 Attendance -Timekeeping | Forms | Others | Incomplete Logs | Jayson
1.5 Attendance -Timekeeping | Forms | Others | Batch DTR Entry | Jayson
1.5 Attendance -Timekeeping | Forms | Others | CTO Entry | Jayson
1.6 Leave Administration | Forms | Fig. 1.6.1 Request for Absence - Job-Order | Request for Absence | Richard
1.6 Leave Administration | Forms | Fig. 1.6.2-a Application for Leave Form | Leave Application | Richard
1.6 Leave Administration | Forms | Fig. 1.6.2-b.1 Application for Leave List | Leave Application | Richard
1.6 Leave Administration | Forms | Fig. 1.6.2-b.2 Application for Leave Print List | Leave Application | Richard
1.6 Leave Administration | Forms | Fig. 1.6.2-b.3 Application for Leave | Leave Application | Richard
1.6 Leave Administration | Reports | Fig. 1.6.3 Employee Leave Credits and Accumulation Report | Leave Ledger | Richard
1.6 Leave Administration | Reports | Fig. 1.6.4 Leave Balance Summary Report | Leave Balance Summary Report | Richard
1.6 Leave Administration | Forms | Others | Leave Approval | Richard
1.6 Leave Administration | Forms | Others | Leave Cancellation | Richard
1.6 Leave Administration | Forms | Others | Leave Credits/Beginning Balance Entry | Richard
1.7 Retirement and Other Personnel Services / Benefits | Forms | Fig. 1.7.1-a Approval & Acceptance of Retirement or Resignation | Retirement and Separation
1.7 Retirement and Other Personnel Services / Benefits | Forms | Fig. 1.7.1-b Clearance (Resignation/Retirement) | Retirement and Separation
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.2 Evaluation Worksheet on Accumulated Leave Credits | Evaluation Worksheet
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.3 Computation of Terminal Leave | Computation of Terminal Leave
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.4 Certification of Employment (Permanent/Casual & JO) | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.5 Service Record Generic (Permanent & JO) | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.6 Service Record GSIS | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.7 Service Length | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.8 Training Certificates | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.9 Increment List / Schedule | Inrement Schedule
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.10 Loyalty List/Schedule | Loyalty List
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.11 Step Increment List | Step Increment List
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.12-a Notice of Salary Adjustment | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.12-b Salary Adjustment Report | Salary Adjustment Report
1.7 Retirement and Other Personnel Services / Benefits | Reports | Fig. 1.7.12-c Notice of Step Increment | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.13 Employee Summary Count | Employee Summary Count
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.14 Employee Master List | Employee Master List
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.15 Department/Office List | Department Profiling
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.16 Memo’s and Violations | Memos and Violations
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.17 -a Memo’s Offenses Set (2017 RACCS) | Memos and Violations
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.17 -b Memo’s Offenses Set (2017 RACCS) | Memos and Violations
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.17 -c Memo’s Offenses Set (2017 RACCS) | Memos and Violations
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.17 -d Memo’s Offenses Set (2017 RACCS) | Memos and Violations
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.18-a Agency Remittance Advice Form A | Agency Remittance
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.18-c Agency Remittance Advice Form C | Agency Remittance
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.18-d Agency Remittance Advice Form D | Agency Remittance
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.18-e Agency Remittance Advice Form E | Agency Remittance
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.19 Notice of Violations (TOP Type) | Employee Profiling
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.20 ID Generation | ID Generation
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.21 Organizational & Functional Chart | Organizational & Functional Chart
1.7 Retirement and Other Personnel Services / Benefits | Employee Profile: | Fig. 1.7.22 Drug Test Tagging and Monitoring | Drug Test Entry and Monitoring
1.8 Complaints |  | Fig. 1.8.1.1 Complaint Form | Complaint Form
1.8 Complaints |  | Fig. 1.8.1.2 Incident Report Form | Incident Report Form
1.8 Complaints |  | Fig. 1.8.1.3 Certification of Non-Forum Shopping | Complaint Form
1.8 Complaints |  | Fig. 1.8.1.4 Minutes of Meeting | Minutes of the Meeting
1.8 Complaints |  | Fig. 1.8.1.5 Resolution/Decision | Resolution/Decision
1.8 Complaints |  | Fig. 1.8.2.1 Grievance Form | Grievance Form
1.8 Complaints |  | Fig. 1.8.2.2 Grievance Agreement Form | Grievance Form
1.8 Complaints |  | Fig. 1.8.2.3 Certificate of Final Action on the Grievance | Grievance Form
1.8 Complaints |  | Fig. 1.8.2.4 Minutes of Meeting | Minutes of the Meeting
1.8 Complaints |  | Fig. 1.8.2.5 Resolution/Decision | Minutes of the Meeting
1.9 Citizen’s Charter |  | Fig. 1.9.1-a Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-b Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-c Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-d Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-e Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-f Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-g Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-h Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-i Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-j Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-k Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-l Citizen’s Charter | Citizen’s Charter
1.9 Citizen’s Charter |  | Fig. 1.9.1-m Citizen’s Charter | Citizen’s Charter